## Slide 1: The Dam Removal Process and The Role of the Project Manager
Dam Busters 101
November 1, 2023

## Slide 2: Massachusetts Division of Ecological Restoration (DER)
State agency, part of Dept. of Fish and Game
27 staff
4-person dam removal program
Also coastal wetland restoration, freshwater wetland restoration, culvert upgrade grants…
Presentation is based on our experiences

## Slide 3: The Dam Removal Process and the Role of the Project Manager
1. The role of the project manager
2. Overview of the dam removal process
3. Discussion
Audience:
Municipal or non-profit organization staff that are planning to manage a dam removal project
Hopewell Mills Dam Removal,
Mill River, Taunton, 2012

## Slide 4: Massachusetts has more than 3000 dams
Owned by towns, private companies, individuals, NGOs, the state…
Small % provide drinking water, flood control, regional recreation
Most built to power mills in the 1700s-1800s
~70 removed in last 15 years

## Slide 6
Notes: An overwhelming majority were built a LONG time ago for purposes like this...

## Slide 8: Billerica Dam / Talbot Mills Dam, Concord River
The Oldest Dams Were Controversial When Built

## Slide 9: Timeline
“Mere shad, armed only with innocence and a just cause…I for one am with thee, and who knows what may avail a crowbar against that Billerica Dam?”
-- Henry David Thoreau, 1839
“For generations, a painful and expensive controversy has existed in relation to the [Billerica Dam, and if not removed now, the children, and children’s children of these parties will be cursed with strife and contention”
-- Henry French speaks to the Massachusetts legislature in 1861
Billerica Dam, Concord River
1710 – dam constructed
1711 – first lawsuit
1722 – dam removed – rebuilt – removed by force – rebuilt
1723 – agreement to open spillway for two months for fish migration
1798 – lawsuit
1828 – dam built higher
1860 – lawsuit
2000s – consideration for fish passage or removal
2023 – moving towards removal

## Slide 10
Most dams in MA were originally built to power mills.
20th Century: Dam Abandonment

## Slide 11: 2. Others enjoy benefits of the dam
Waters lawn
Owns a kayak
Watches birds
Loves the view
Common Functions of Dams Today
Road / utility corridor

## Slide 12
21st Century: Dam Removal

## Slide 13: The role of the dam removal project manager: Part 1

## Slide 14: The Role of the Dam Removal Project Manager

## Slide 15: The project manager should…
Provide leadership
Coordinate tasks described in this training
Delegate to project partners (if applicable) and consultants
Serve as point of contact
Track progress
Call on experts
Build partnerships
Maintain sense of humor!

## Slide 16
1. Dam owner wants to remove dam
2. Project Scoping
3. Cost / feasibility assessment
4. Engineering & Design Process
4. Permitting
Final Construction Plans and Permits
Bid Process / Contracting
Dam Removal!!!
5. Fundraising
The Process

## Slide 17: Project Scoping – led by Project Manager
Mill Street Dam, Pittsfield
Ownership of dam
Infrastructure (utilities, buildings, roads, walls)
Likelihood of sediment contamination
Other uses of impoundment
Traditional Knowledge of River
Habitat benefit (of dam; of removal)
Potential recreation benefits of removal
Notes: Private or municipal dam owners can do a dam removal themselves and streamline the process. If the project is a proactive, partnership based restoration project, then there are fundraising and community outreach throughout the process. Fundraising takes time.

## Slide 18
Mill Street Dam, Pittsfield

## Slide 19: 3. Cost / Feasibility Assessment
Should be based on project scoping
Target key issues of concern
May incorporate community concerns
Notes: Private or municipal dam owners can do a dam removal themselves and streamline the process. If the project is a proactive, partnership based restoration project, then there are fundraising and community outreach throughout the process. Fundraising takes time.

## Slide 20
Mill Street Dam, Pittsfield

## Slide 21
1. Dam owner wants to remove dam
2. Project Scoping
3. Cost / feasibility assessment
4. Engineering & Design Process
4. Permitting
Final Construction Plans and Permits
Bid Process / Contracting
Dam Removal!!!
5. Fundraising
The Process

## Slide 22
4. Engineering and Design Process
survey of dam, impoundment, upstream, downstream, utilities
wetland delineation and estimate of change
evaluation and testing of sediment
structural review of dam and adjacent infrastructure (walls, bridges, buildings, etc.)
water level studies
cultural resource inventory
coordination with Natural Heritage re: sensitive species

## Slide 24
1. Dam owner wants to remove dam
2. Project Scoping
3. Cost / feasibility assessment
4. Engineering & Design Process
4. Permitting
Final Construction Plans and Permits
Bid Process / Contracting
Dam Removal!!!
5. Fundraising
The Process

## Slide 25: Permitting
MEPA
Notice of Intent to Conservation Commission
401 Permit (DEP)
Chapter 91 Dredge Permit (DEP)
404 permit (an abbreviated form)
Project Notification Form to Massachusetts Historical Commission
Chapter 253 Dam safety permit (if Jurisdictional Dam)

## Slide 26: Construction bidding and contracting

## Slide 27
1. Dam owner wants to remove dam
2. Project Scoping
3. Cost / feasibility assessment
4. Engineering & Design Process
4. Permitting
Final Construction Plans and Permits
Bid Process / Contracting
Dam Removal!!!
5. Fundraising
The Process

## Slide 28: The Dam Removal Process and the Role of the Project Manager
1. The role of the project manager
2. Overview of the dam removal process
3. Discussion
Audience:
Municipal or non-profit organization staff that are planning to manage a dam removal project
Hopewell Mills Dam Removal,
Mill River, Taunton, 2012